Below is a sample of how we set up our timeline.

# October:

Have an awards submission meeting

### Assign Job:

  - Submissions - writers, editors

    - Impact Award

    - Woodie Flowers Award

    - Dean’s List

  - Executive Summary - writers, editors

  - Videos - editors, filmographers, interviewers

  - Business plan - writers, editors

#### Set up deadlines for :

  - Impact Outline

  - First Draft of Impact  Award

  - Second Draft of Impact Award

  - Third Draft of Impact Award

  - Final Draft of Impact Award

  - Woodie Flowers Award Outline

  - First Draft of Woodie Flowers Award

  - Second Draft of Woodie Flowers Award

  - Third Draft of Woodie Flowers Award

  - Final Draft of Woodie Flowers Award

  - Dean’s List Outline

  - Dean’s List First Draft

  - Dean’s List Second Draft

  - Dean’s List Third Draft

  - Dean’s List Final Draft

  - Presentation Outline

  - Presentation First Draft

  - Presentation Second Draft

  - Presentation Final Draft

Work on Storyboard for Safety Animation Video - Be sure to check the FIRST site for the “Theme” of the video it changes annually

# November:

#### Week 1-

  - Impact Award outline

  - Presenters picked

  - Impact video idea brainstorming

  - Begin creating Safety Animation Award

  - Make sure that your Deans List Students and Woodie Flowers nominees have a FIRST Dashboard account and a signed Consent and Release form in their profile

#### Week 2 -

  - 1st draft of Chairman’s Award submission

  - Choose Woodie Flowers Award and Dean’s List nominees

  - Begin gathering information for Business Plan

  - Finalize Safety Animation Award

# December:

Safety Animation Video due early in the month

#### Week 1 -

  - 2nd draft of Impact Award submission

  - Outline for Impact  Award Presentation and Woodie Flowers

  - Video storyboard

  - 1st draft of Executive Summary and Essay

  - Submit the Safety Animation Award

  - Compile your Documentation sheet and get ready for submission

#### Week 2 -

    - 1st draft of Impact Presentation, Dean’s List, and Woodie Flowers nomination

    - Begin Impact  video recording and draft of Business Plan

# January:

#### Week 2 -

  - 3rd draft of Impact Award submission

  - 2nd draft of Impact Award presentation script, Dean’s List & Woodie Flowers

  - Begin editing the Impact Award video

  - Pick pictures for Impact Award, Woodie Flowers and Deans List submissions.

  - Finalize your Documentation sheet and get ready for submission

#### Week 3 -

  - Edit Impact Award submission as a team

  - 3rd draft of Impact  presentation

  - Pick Dean’s list & Woodie Flowers nominees

  - Continue Impact video

#### Week 4 -

  - Go over Woodie Flowers Award as a team

  - Finalize Dean’s List nominee

  - Get input on video from team members

  - Make final edits to submission and presentation

# February:

#### Week 1 -

  - Work on the final drafts of  Impact  submission, Dean’s List and Woodie Flowers nominees

#### Week 2 -

  - Submit all awards, Impact, video link and documentation, Woodie Flowers nominee , pictures and Dean’s List nominee